## Read me
Fund, Fix or Stop: editable templates
Companion to the book. Copy and adapt these templates for use within your own organization.
Topic | Notes
How to use | Yellow cells are inputs. White cells with formulas calculate automatically. Each sheet has one example row from the book's fictional bank, Fytvio; replace it with your own data.
Status colors | Status is always written as text (Green, Amber, Red) so that it survives printing and color-blind viewing.
Defaults | Limits shown are the book's default starting points. Your signed threshold sheet sets the actual limits.
What to customize | Every yellow cell, plus the limits, sample sizes, deadlines and the delegated funding limit, which the book gives only as defaults.
Blank or example | Sheets named Example hold completed records for the fictional bank. Every other sheet is a blank template.
Self-assessment | Chapter 1. Ten questions and a score.
Inventory | Chapter 3. One row per use case: the twelve fields, the contract renewal date, and whether the investment is mandatory.
Explore entry | Chapter 13. One-page scoring of new ideas; eligibility and ranking are calculated.
Intake and tiering | Chapter 4. Six answers; the highest sets the tier.
Threshold sheet | Chapter 11. Limits, readings, and status by rule, including the trend rule with a minimum decline.
Five-test scorecard | Chapter 7. Overall status is the weakest test.
Value leakage | Chapter 9. Business case, four leaks, measured and realized value.
Monthly cost report | Chapter 10. Unit cost against plan with default Economics status.
Leadership page | Chapter 14. Spend by status from a list of investments.
Gate decision | Chapter 13. Record of a fund, fix once, or stop decision.
Red decision memo | Chapter 14. The five sections of the memo.
General tool value plan | Chapter 17. Role-based hypotheses and task-sampling results.
Vendor checklist | Appendix D. Due-diligence questions, what each answer decides, and the vendor's answers.
90-day tracker | Chapter 15. Activities, owners, and dates.
Charter | Chapter 2. Review board charter, with the book's example beside each section.
Discovery checklist | Chapter 3. Quarterly sweep for AI that registration missed.
Gateway controls | Chapter 5. Control checklist per use case, and the model selection record.
Agent approval | Chapter 6. Agent approval record and promotion checklist.
Quality plan | Chapter 8. Test set, live sample, reviewers and grader.
Value plan | Chapter 9. Baseline, comparison, calculation, payback and Finance confirmation.
Recovery and incident | Chapter 12. Recovery plan and incident record.
Example sheets | Three completed records from Appendix A, filled in for Fytvio: a threshold sheet, a Red decision memo, and a value confirmation with live formulas. They show the level of detail that lets a record stand as evidence.

## Self-assessment
AI portfolio self-assessment (Chapter 1)
Answer Yes only if you could show the evidence to an auditor this week. Partly counts as No.
# | Question | Yes / Partly / No
1 | Do you have one list of every AI system in use, including AI features in software you already own? | Partly
2 | Does every AI investment have a named business owner who is accountable for its results? | No
3 | Was a baseline measured before launch for your largest AI investments by spend? | No
4 | Is adoption measured as the share of eligible work done with AI, instead of licenses assigned? | No
5 | Is quality measured on live use, at least monthly, by people who did not build the system? | No
6 | Are serious errors counted separately, so a good average cannot hide them? | No
7 | Is cost tracked per transaction for each investment, as well as in total? | No
8 | Were Green, Amber, and Red limits agreed and signed before each investment went live? | No
9 | Is status confirmed by someone other than the team that runs the investment? | No
10 | Is value reported to leadership as realized only after Finance has confirmed it? | Yes
Yes answers
Reading

## Inventory
AI inventory (Chapter 3)
One row per use case. Low tier needs fields 1-7, 9, and 12.
Inventory no. | 1 Use case and purpose | 2 Business and technical owner | 3 Model, vendor, version | 4 Hosting channel | 5 Data classification | 6 Risk tier | 7 Approval date and conditions | 8 Threshold sheet link | 9 Monthly cost ($) | 10 Users and volume | 11 Value baseline and target | 12 Next review | 9 Contract renewal and notice date | Mandatory? Requirement it meets
FYT-014 | Answers customer questions on fees, payments, and card disputes | Head of customer services / customer platforms engineering lead | Mid-size hosted model, version pinned, vendor under a data processing agreement | AI gateway; vendor cloud, US region | Confidential customer financial data | High | Approved with conditions: AI disclosure to customers; kill switch; 150 sampled monthly | Threshold sheet v2 | 27000 | 420 agents plus customer chat; about 150,000 conversations a month | Baseline: 6 min 20 s handle time; target: 60-second reduction | Quarterly | Vendor contract renews each January; 90 days' notice | No

## Intake and tiering
Intake and risk tiering (Chapter 4)
Choose Low, Medium, or High for each factor. The highest answer sets the tier.
Factor | Low | Medium | High | Answer
1. What data does it use? | Public or internal | Confidential business data or staff personal data | Customer personal or financial data, regulated or partner data | High
2. Who sees or is affected by the output? | Internal team | Enterprise-wide or partners | Customers or the public | High
3. Does it inform, influence, or make decisions? | Informs a person | Influences operations | Credit, account, or financial outcomes | High
4. Can it act without a person approving? | Suggests to the user only | Drafts for others, with approval | Acts on its own | Medium
5. Which vendor and model? | Approved platform | Approved vendor, catalog model new to this use | New vendor, or model outside the catalog | Low
6. How many users, and what volume? | One team | Multiple departments | External or high volume | High
Tier (highest answer)
Number of High answers
Turnaround target (business days)
Item | Entry
Request name and inventory number | Complaint outcome letters to customers (FYT-031)
Business owner and technical owner | Head of complaints / correspondence platform lead
Decision and date | Approve with conditions
Conditions (each with owner and date) | Specialist approves every letter; outcome sentence from complaints system; 100 letters sampled monthly
Mandatory? If yes, the requirement it meets | No
Data readiness: available and owned; quality measured; use permitted | Complaint records available and owned by complaints team; quality checked; use permitted under existing terms
Layer: use case under a standard profile, or governed investment | Governed investment (High tier; output reaches customers)
Threshold sheet signed (governed investments) | Yes

## Explore entry
Explore entry scorecard (Chapter 13)
Score each idea Low, Medium, or High. Low strategic fit, no business owner, or data not ready means it does not enter. Mandatory investments skip the ranking. Check the record of stopped ideas first: a proposal with the same purpose must show what has changed since the stop.
Idea | Business owner | Business objective | Strategic fit | Size of value | Feasibility | Risk | Data ready? | Mandatory? | Eligibility | Rank score | Rank
Mortgage document checks | Head of mortgage operations | Faster mortgage decisions | High | High | Medium | Medium | Yes | No
Branch queue forecasting | Head of branch network | Lower branch staffing cost | Medium | High | High | Low | No | No
Suspicious activity report drafting | Head of financial crime | Meet reporting obligations | High | Low | Medium | High | Yes | Yes
Rank score is size of value plus feasibility (Low 1, Medium 2, High 3). Risk does not rule an idea out; it sets what Explore must prove.

## Threshold sheet
Threshold sheet and status rules (Chapter 11)
Direction: Higher if bigger is better, Lower if smaller is better. Red limit is the edge of the Red zone; leave it blank for leading signals, which set Amber at most. Leave readings blank if not collected.
Measure | Direction | Baseline | Green limit | Red limit | Min. sample | Min. decline | This period | Last period | Two periods ago | Sample size | Limit / data status | Trend | Type | Reason for the limits | Source and frequency
Live accuracy (%) | Higher | 92 | 90 | 86 | 150 | 2.5 | 91 | 92 | 93 | 150 |  |  | Performance limit | Green allows about two points of sampling variation below the 92% baseline; Red just below the bottom of the sampling range for 150 samples | Reviewer-scored live sample, monthly
Critical errors reaching customers | Lower | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | Hard constraint | Customer-facing and High tier: any one is Red, no Amber band | Live sample, complaints, and grader flags, daily
Override rate (%), leading signal | Lower | 12 | 15 |  |  | 1 | 13 | 12 | 12 |  |  |  | Leading signal | Moves before accuracy does; sets Amber at most | Gateway, weekly owner check
Retrieval miss rate (%), leading signal | Lower | 4 | 6 |  |  | 1 | 4 | 4 | 4 |  |  |  | Leading signal | Moves before accuracy does; sets Amber at most | Gateway, weekly owner check
Unit cost per conversation ($) | Lower | 0.18 | 0.198 | 0.225 |  | 0.005 | 0.205 | 0.19 | 0.18 |  |  |  | Performance limit | Default limits: 10% and 25% above the $0.18 plan, not rounded | Cost metering, reconciled with the ledger monthly
Response time, 95% of answers within (s) | Lower | 3.1 | 4 | 6 |  | 0.2 | 3.3 | 3.2 | 3.1 |  |  |  | Performance limit | Set from the 3.1-second baseline | Gateway, daily
Overall status (lowest on the sheet)
A missing reading counts as missing data: report it as Amber. A critical event is Red the same day.
Sampled measures: a single reading below Green sets a watch and the next sample is doubled; a second low reading confirms Amber. A reading whose whole range sits below the Red limit is Red at once.
Trend: a third consecutive decline is Red, whether or not a recovery plan exists. Add earlier periods to the sheet to track it.

## Five-test scorecard
Five-test scorecard (Chapter 7)
Overall status is the weakest test. Use a dash for tests not scored at this stage.
Item | Entry
Investment, inventory number, and stage | Small-business lending agent (FYT-052), Pilot
Business owner | Head of business banking
Reporting period | Month 2
Test | Headline measure and limit | This period | Last period | Status | Cause (if Amber or Red)
Value | Rep time saved vs control; target 6 h/week | 5.5 h | 5.2 h | Green
Adoption | Share of eligible follow-ups; target 80% | 88% | 84% | Green
Trust | Live accuracy 92%; zero critical | 94%; 23 critical, one cause | 93%; 0 | Red | Outdated rate quotes sent to 23 businesses
Economics | Cost per email vs $0.10 plan | $0.09 | $0.09 | Green
Delivery | Milestone slip 2 weeks or less | On schedule | On schedule | Green
Overall | Weakest test

## Value leakage
Value measurement and leakage (Chapter 9)
Annual figures in dollars. Leaks are entered as positive amounts.
Line | Annual value ($) | Cause | Owner
Business case (net benefit) | 10000000 | Net of planned running cost | Business owner
Adoption gap | 2400000 | Two lines of business not connected; handwritten forms routed around | Business owner
Process not redesigned | 1500000 | Full field check kept | Operations
Quality rework | 900000 | Handwritten form extraction errors | Delivery team
Cost overrun | 700000 | Largest model used for every document | Delivery team
Measured net benefit
Measured as share of business case
Full running cost (planned plus overrun) | 1700000
Classification of gross benefit | Annual value ($) | Evidence
Harvested | 2400000 | 20 vacant positions not refilled
Redeployed | 1200000 | Loan-processing backlog reduced by a measured amount
Unharvested | 2600000 | Capacity created, not yet used for named work
Realized gross (harvested plus redeployed, Finance-confirmed)
Realized net (gross less full running cost)
Realized net as share of business case
Value test on realized net (default limits)
Check: classes add up to gross benefit

## Monthly cost report
Monthly cost report (Chapter 10)
One use case per copy of this sheet. Dollars per month.
Item | Plan | Actual | Variance
Completed transactions | 150000 | 200000
Model usage ($) | 10500 | 19000
Share of platform cost ($) | 7500 | 10000
Licenses ($) | 3000 | 4000
Support effort ($) | 6000 | 8000
Total cost ($)
Unit cost ($ per transaction)
Economics status (default limits)
Forecast variance over 15%?

## Leadership page
Monthly leadership page (Chapter 14)
List every investment with its annual spend and overall status.
Investment and stage | Annual spend ($) | Overall | Tests not Green | Decision or help needed
Customer service assistant (Run) | 400000 | Amber | Economics | Fix: unit cost 14% over plan
Document intake (Scale) | 1700000 | Red | Value; Adoption; Economics; Delivery | Fix: leakage review; 19% realized net
Fraud model (Run) | 900000 | Amber | Trust | Fix: precision down two months
Coding assistant (Run) | 1200000 | Green
Total spend ($)
Share of spend in Green
Share of spend in Amber
Share of spend in Red
Red spend target (10% or less) met?

## Gate decision
Gate decision record (Chapter 13)
Item | Entry
Investment, inventory number, and tier | Contract review (FYT-077), Medium
Gate | Explore to Pilot
Criteria agreed at the start of the stage (date) | 90% on 300-clause test set; baseline captured
Evidence against each Green criterion | 92% on second iteration; baseline 3.5 hours per contract
Evidence against each stop criterion | Target met; stop criterion not triggered
Five-test status at the gate | Trust Green (test set); Delivery Green
Decision | Fund
If fix: actions, owner, and end date
If fund: next-stage budget cap, end date, Green and stop criteria | $250,000; four months; review time 30% lower than control
If stop: retirement steps, budget returned, lessons recorded
Decided by, date, and dissent | Governance lead and sponsor

## Red decision memo
Red decision memo (Chapter 14)
One to two pages. Circulate before the review board meeting.
Item | Entry
Investment, stage, and inventory number | Chat tools, three (Run)
Cause and evidence | Three tools doing the same job; 2,300 licenses, about 900 weekly users; no baseline
Options (fix: cost and timing; stop: write-off and money released) | A keep all; B consolidate to one tool (about $450,000 a year); C stop all
Customer impact, and risk impact | Option B moves all use under the strongest data terms
Recommendation | Option B, migration within 90 days
Decision needed by | Next review board meeting
Decision, date, and dissent (after the meeting)

## General tool value plan
General-purpose tool value plan (Chapter 17)
One row per role group. Times are minutes per task from task sampling or the cohort comparison.
Role group | Named task | Minutes without | Minutes with | Change | Measurable? | Decision
Credit analysts | Credit memo on a loan application | 35 | 26 |  | Yes | License
Finance analysts | Monthly variance commentary | 90 | 72 |  | Yes | License
Service supervisors | Call quality notes | 20 | 17 |  | Yes, smaller | License
HR advisers | Replies to policy questions | 12 | 11 |  | No | Request pool only
Seats |  | 950
Price per seat per month ($) |  | 30
Annual cost ($)
Note on C18: Illustrative price from the book. Use your contracted price.

## Vendor checklist
Vendor due-diligence questions (Appendix D)
Not legal advice. Review answers with Procurement and Legal.
Area | Question | What the answer decides | Vendor answer | Acceptable?
Data use | Is our data used to train or improve your models? Can that be excluded in the contract? | Which data classes the platform may receive
Retention | How long are prompts, outputs, and logs kept, and can we set the period? | The data classes allowed and the contract retention clause
Location | Where is our data processed and stored, and which subprocessors are involved? | Whether data residency rules are met
Security | Which independent security assessments can you share? | Whether the security review can rely on them or must test itself
Regulated data | Will you sign the data protection terms our regulators require for customer data? | Whether customer data may be used at all
Model changes | How much notice before a model version changes or is retired? Can we test first? | The fallback plan and the budget for re-testing
Evidence | Can we run our own test set before signing? | Whether the Trust test can be scored before purchase
Reporting | Can usage and cost be reported by our use case or department? | How cost is allocated on the threshold sheet
Incidents | How quickly will you notify us of a security or quality incident? | Whether the incident process can meet its own deadlines
New features | Can new AI features be kept off until we enable them? | Whether new features can wait for intake
Continuity | What happens to our service if your model is withdrawn, your service fails, or your company leaves the market? | The manual fallback and the exit budget
Exit | Can we export our data, prompts, and configurations if we leave? | How much lock-in the portfolio review must price in
Answers marked No or Needs follow-up

## 90-day tracker
90-day plan tracker (Chapter 15)
Days | Activity | Owner | Done
1-14 | Governance lead confirmed; review board charter approved
1-30 | Inventory built from invoices, contracts, expenses, sign-on records, scans
1-30 | Spend baseline set; owner assigned to every entry
1-30 | Current review processes mapped
21-30 | Top 20 investments by spend agreed
31-45 | Intake and tiering launched in the existing intake form
31-60 | Gateway logging, tagging, and identifier checks switched on
31-45 | Model catalog and measure definitions published
31-60 | Threshold sheets signed for the top 20
31-60 | Data sources connected for monthly status
61-80 | First test sets and live samples for High-tier systems
61-90 | Weekly owner checks started
75-85 | Status rules applied; first monthly health report issued
85-90 | First portfolio review; fund, fix, and stop decisions recorded
Activities done

## Charter
AI review board charter (Chapter 2)
The charter should fit on one page. Write your entry in the yellow column; the right-hand column shows the book's fictional example.
Section | What to write | Your entry | Example (Fytvio)
Purpose | Why the review board exists, in one or two sentences |  | Approve, oversee, and make funding recommendations on all AI used at Fytvio
Scope | Which AI is covered |  | Platforms and the uses on them; built, bought, embedded SaaS features, agents, existing ML models
Boundary | What stays with existing reviews |  | Business case, architecture fit, contracts, data rights
Chair and members | Named roles, not people |  | Chief data and AI officer (chair); chief risk officer (co-chair, veto on risk); CISO; CPO; Compliance; Finance; Enterprise Architecture; business-unit AI leads attend for their items
Secretary | Who runs the review board |  | AI governance lead
Independence | Reporting line of the governance lead; role of internal audit |  | Governance lead reports to the chief risk officer; internal audit observes and reviews annually
AI policy and exceptions | Policy owner; how exceptions are approved and tracked |  | AI policy approved by the executive committee; exceptions with expiry dates, reported quarterly
Quorum | Minimum attendance to decide |  | Chair or delegate, co-chair or delegate, plus security and privacy, plus a majority of members
Decision rights | What the review board decides; what is delegated |  | Board: platforms, High-tier investments, Red decisions, pause or retire; funds up to $500,000 per stage and recommends above it to the investment committee. Business-unit AI leads: Low and Medium tier in their units. Governance lead: standards, profiles, status
Escalation | Where unresolved issues go |  | Executive committee; funding through its investment committee
Cadence | Meeting schedule |  | Review board every 2 weeks; health review monthly; portfolio review quarterly
Records | Decision record format and storage |  | Decision, conditions, reasons, dissent, evidence, next review date
Performance targets | How the review board is measured |  | The six board measures in Chapter 14
Charter review | When the charter is reviewed |  | Annually, or after any Sev 1 incident

## Discovery checklist
Discovery checklist (Chapter 3)
Run quarterly. Coverage = registered AI systems divided by discovered AI systems; the target is 95 percent or higher.
Discovery sweep
Check | Done? | Date | Notes
Invoices and accounts payable searched for AI vendors.
Corporate card and expense records searched.
New and renewed contracts checked for AI features.
Single sign-on application authorizations reviewed.
Network and proxy logs checked for traffic to AI services.
Cloud accounts scanned for AI services.
Release notes of major software platforms reviewed for new AI features.
Gateway access keys matched to inventory entries.
Coverage calculated and reported; gaps assigned to an owner with a date.

## Gateway controls
Gateway controls and model selection (Chapter 5)
One checklist per use case. Where a control lives outside the gateway, record where in the notes: vendor settings, identity, data-loss prevention, contract or platform logs.
Gateway control checklist (per use case)
Control | In place? | Notes
Inventory number tagged on every call
Personal and financial identifier patterns: redact or block
Prompt injection screening on inputs and retrieved content
Exact cases handled by rules before any model
Approved model class; backup model pinned and passed the test set
Prompt templates versioned; fixed portion cached
Retrieval limited to user entitlements
Tools from approved catalog only; inputs validated; read-only by default
Output format validated
Grounding check for document-based answers
Output checks: hold or stream decision recorded
Document sources: owner, effective and expiry dates, versions, freshness check
Personal-data scan before display
Full trace, tokens, cost, response time, and errors logged
Model version pinned; test set run on every change
Model selection record
Item | Guidance | Entry
Use case and inventory number
Task type (classify, extract, summarize, answer, plan)
Test set and approved threshold
Model classes tested, with accuracy for each
Cost per task and response time for each model class tested
Selected class, model, and pinned version
Reason a lower class was not chosen
Data terms confirmed (agreement, training, retention)
Hosting location and residency
Cost techniques applied
Approved by and date

## Agent approval
Agent approval record (Chapter 6)
Levels 1 and 2 can be approved at intake; Level 3 is earned after two clean periods at Level 2. Recommend-only is fixed at approval for irreversible actions on people or money.
Item | Guidance | Entry
Agent name and inventory number
Business owner and technical owner
Agent identity and systems it can access
Acts for users? Whose rights apply; actions needing more than the user’s rights
Tool servers used, and tools allowed from each
Action types, with autonomy level for each
Tools allowed for each action type
Limits: steps per task, actions per day, spend per day
Reads external content, such as email, customer uploads or web pages? (If yes, no write access) | Yes / No
Memory: what is stored, and for how long
Checkpoints required before which actions
Handoff triggers and handoff summary format
Reversal procedure tested (date)
Critical errors defined
Measures: steps per task; actions reversed or blocked; plus five tests
Promotion criteria and step-down rule
Kill switch tested (date)
Approved by, date, and next review
Promotion checklist
Check | Met? | Date | Notes
Two consecutive review periods within all limits at the current level.
No critical errors in either period.
Steps per task and actions reversed or blocked stable or improving.
Reversal procedure tested for the new level (if moving to Level 3). Recommend-only is fixed at approval and is not a promotion.
Threshold sheet updated with limits for the new level.
Review board decision recorded, with the scope of the promotion stated by action type.

## Quality plan
Quality measurement plan (Chapter 8)
Sampling ranges use the 95 percent Wilson score interval by default. Grader calibration is a minimum condition, not proof of reliability.
Item | Guidance | Entry
Use case and inventory number
Test set: size, composition, and who approved the answers
Test set: run triggers (every change; monthly) and refresh date
Live sample: size and frequency for the tier, and stratification by topic
Minimum samples for high-risk topics
Reviewers (names or team) and confirmation they are independent
Scoring guide version; definition of acceptable | Passes correct, complete, grounded, safe
Double-scoring: at least 50 items, pooled if needed; agreement target | Kappa 0.6 or more, with percentage
Automated grader: scope, calibration date, agreement with humans | Decides status only at kappa 0.6 or more
Critical, major, and minor errors defined for this use case
Segment limits (if any)
Safety signals monitored (identifier blocks, injection attempts, output scan)
Bias testing scope and schedule (High tier)
Where results are recorded and who confirms them

## Value plan
Value measurement plan (Chapter 9)
Value counts as realized only when Finance confirms it, net of full running cost. Mandatory investments are scored on meeting the obligation.
Item | Guidance | Entry
Use case and inventory number
Benefit types (time, errors, revenue, recoveries, risk)
Baseline period (4–8 weeks) and dates
Baseline: time per task, error rate, volume by type
Comparison method (control group or adjusted before-and-after)
Control group description and matching
Calculation formula and adoption adjustment
Loaded cost per hour (agreed with Finance)
One-time cost (Explore, Pilot, build, integration) and expected payback
Process changes required, owner, and date
Expected classification: harvested, redeployed, unharvested
Named work for redeployed capacity and how its output is measured
Finance contact and quarterly confirmation dates
Current confidence level (modeled, measured, realized)

## Recovery and incident
Recovery plan and incident record (Chapter 12)
A recovery plan is due within 5 business days of Amber. A third consecutive decline is Red, whether or not a recovery plan exists.
Recovery plan
Item | Guidance | Entry
Use case and inventory number
Status and rule triggered (date)
Cause (or work to find it)
Actions, each with owner and date
Measures that will show the fix worked
Target date to meet limits
Five conditions: root cause; fix tested; live results hold (2 periods); signals stable; governance lead confirms | Date each met
Escalation date if target is missed
Incident record
Item | Guidance | Entry
Incident number, use case, and severity
Time detected, and how
Containment action and time
Users notified (time)
Affected interactions and people identified
Corrections made and people contacted
Compliance decision on reporting
Root cause
Test cases added; test set result before re-enabling
Why detection took as long as it did
Monitoring and limit changes
Re-tiering or re-approval needed?
Closed by (governance lead) and date

## Example threshold sheet
Completed threshold sheet: customer service assistant (Chapter 11)
Completed example from Appendix A, for the fictional bank Fytvio. Use it as a guide to the level of detail; record your own in the blank template.
Item | Entry
Use case | Customer service assistant. High tier. Run stage.
Signatures | Business owner (head of customer services) and AI governance lead, signed and dated. Review board approval recorded in its minutes.
Version | Version 2. Re-approved after the test set was rebuilt (Chapter 8). Version 1 kept on file.
Exceptions in force | None.
Critical errors reaching customers | Hard constraint. Any one is Red, with no Amber band. Reason: the assistant is customer-facing and High tier. Source: live sample, complaints and grader flags, checked daily.
Live accuracy | Performance limit. Green 90% or higher, Red below 86%. Reason: Green allows about two points of sampling variation below the 92% baseline; Red sits just below the bottom of the sampling range for 150 samples. Minimum sample 150 a month; minimum decline 2.5 points. Source: reviewer-scored live sample, monthly.
Test-set accuracy | Performance limit. Green 92% or higher, Red below 89%. Reason: set from the 94% baseline on 400 cases. Source: evaluation service, on every change and monthly.
Share of eligible questions handled | Performance limit. Green 70% or higher, Red below 52.5%. Reason: default limits, 75% of the 70% target for Red, not rounded. Source: contact center system, monthly.
Unit cost per conversation | Performance limit. Green $0.198 or lower, Red above $0.225. Reason: default limits, 10% and 25% above the $0.18 plan. Source: cost metering, reconciled with the ledger monthly.
Response time | Performance limit. 95% of answers within 4 seconds is Green; above 6 seconds is Red. Reason: set from the 3.1-second baseline. Source: gateway, daily.
Handle-time reduction | Performance limit. Green 54 seconds or more, Red below 42 seconds. Reason: set from the 60-second target. Source: contact center system against the baseline; turned into realized value by Finance each quarter.
Override rate and retrieval miss rate | Leading signals. Above 15% and above 6% set Amber at most. Reason: they move before accuracy does. Source: gateway, weekly owner check.

## Example Red memo
Completed Red decision memo: small-business lending agent (Chapter 14)
Completed example from Appendix A, for the fictional bank Fytvio. Use it as a guide to the level of detail; record your own in the blank template.
Section | Content
Investment | Small-business lending agent (FYT-052). Pilot stage, month 2. Level 2: a relationship manager approves each email.
Cause and evidence | The agent took rates from a document library that still held last quarter's rate sheet. The monthly live sample found one wrong quote; gateway logs found all 23 within two hours. Quotes were 0.25 to 0.5 percentage points too low. Approvals missed them because emails were approved in batches, some 30 or more in a few minutes.
Status | Red the same day under the critical event rule. Agent paused. Other tests Green: value 92% of target, adoption 88%, cost below plan.
Option 1: fix once | Take rates from the pricing system, add 40 test cases, limit batch approval to ten emails and open every email with a price. Cost: team time and two more months of pilot running cost. Timing: two months to show the fix holds.
Option 2: stop | Write off pilot spend to date and return the remaining pilot budget to the portfolio pool. The time saving of about 5.5 hours a week per manager is lost.
Customer and risk impact | 23 businesses received wrong quotes; each was called with a corrected quote. Handled as a Sev 1 incident. Compliance is reviewing fair lending and state-law exposure.
Recommendation | Fix once. The cause is specific and testable, and the fix removes the model from writing rates.
Decision needed by | Ten business days from the Red status.
Decision and dissent | Fix once, as recommended, with two months to show it holds. Dissent recorded: one member asked for a stop, on the grounds that Level 2 approval had failed and might fail again.

## Example value confirmation
Completed value confirmation: document intake (Chapter 9)
Completed example from Appendix A, for the fictional bank Fytvio. Yellow cells are inputs; the rest calculate, so the example can be reused with your own figures.
Line | Value | Evidence or note
Baseline minutes per document | 6 | Measured for six weeks before launch
Planned minutes per document | 2 | Business case
Documents per year | 2500000 | Baseline period, annualized
Loaded cost per hour ($) | 66 | Agreed with Finance in advance
Planned running cost per year ($) | 1000000 | Business case
Business case gross benefit ($) |  | Minutes saved, in hours, times the loaded cost
Business case net benefit ($)
Leak (annual, entered as positive) | Value | Cause
Adoption gap | 2400000 | 78% of eligible documents went through the system
Process not redesigned | 1500000 | Full field check kept
Quality rework | 900000 | Handwritten form extraction errors
Cost overrun | 700000 | Largest model used for every document
Measured net benefit ($) |  | First Finance review, two quarters into Scale
Classification | Value | Evidence
Harvested | 2400000 | 20 vacant intake positions not refilled, visible in the budget
Redeployed | 1200000 | Clerks moved to the loan-processing backlog, which fell by a measured amount
Unharvested | 2600000 | Capacity created, not yet used for named work; reported as capacity, not money
Realized gross ($) |  | Harvested plus redeployed, confirmed by Finance at quarter-end
Full running cost ($) |  | Planned cost plus the overrun
Realized net benefit ($) |  | Compared with the net business case
Gross measured benefit ($) |  | Net benefit plus full running cost
Check: classes add up to gross benefit |  | The classes split gross benefit, before running cost
Value-to-cost ratio |  | Floor 1.5 at Scale and Run; Red below 1.0
Measured net as share of business case |  | Sets status at the Scale stage
Realized net as share of business case |  | Sets status from the Run stage
Value test (default limits) |  | On measured value at Scale. Green at 90% or more of the business case; Amber 70 to 89%; Red below 70%
Next confirmation | Next quarter-end, after the four fixes in Chapter 9